## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
1 | 1 | US-01 | As a user, I want to select one of three predefined negotiation scenarios so that I can start the appropriate negotiation setup. | Must Have | None | Hemalatha Bora | 3- Completed
1 | 1 | US-02 | As a user, I want the selected scenario to automatically load its predefined agents, roles, goals, and constraints. | Must Have | US-01 | Mohammad Shaik Fawaz | 3- Completed
1 | 1 | US-03 | As a user, I want to configure each agent's personality using Aggressive, Collaborative, or Risk-Averse. | Must Have | US-02 | Santanu Atta | 3- Completed
1 | 1 | US-04 | As a user, I want to see each agent in a role card containing name, role, goal, constraints, and selected personality. | Must Have | US-02, US-03 | Mohammad Shaik Fawaz | 3- Completed
1 | 2 | US-05 | As the system, I want to create a negotiation state containing scenario, round, turn, offers, status, goals, constraints, and personalities. | Must Have | US-02, US-03 | Santanu Atta | 2- In Progress
1 | 2 | US-06 | As the system, I want a standard offer structure so that all agents use a consistent representation of offers and counteroffers. | Must Have | US-05 | Hemalatha Bora | 2- In Progress
1 | 2 | US-07 | As the system, I want rule-based Accept/Reject/Counteroffer logic based on agent goals and constraints. | Must Have | US-05, US-06 | Mohammad Shaik Fawaz | 2- In Progress
1 | 2 | US-08 | As the system, I want to track concessions across rounds, including direction and size of change. | Should Have | US-06, US-07 | Mohammad Shaik Fawaz | 2- In Progress
1 | 2 | US-09 | As the system, I want an Orchestrator interface that determines the current agent, round, history, state, and next agent. | Must Have | US-05 | Hemalatha Bora | 2- In Progress
1 | 2 | US-10 | As the application, I want scenario and agent configuration data to initialize the negotiation state before the first turn. | Must Have | US-02, US-05 | Santanu Atta | 2- In Progress
1 | 2 | US-11 | As the team, I want the implementation organized and pushed to GitHub with identifiable commits and a README. | Must Have | US-01–US-10 | All Interns | 2- In Progress
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-01 | T-01 | Implement scenario selection module for Vendor Pricing, Job Offer, and Project Budget Allocation. | TBD | TBD | Santanu Atta | Coding | 3- Completed | 4
US-02 | T-02 | Define scenario data: agents, roles, goals, and constraints for all three scenarios. | TBD | TBD | Hemalatha Bora | Design | 3- Completed | 5
US-03 | T-03 | Add personality options: Aggressive, Collaborative, Risk-Averse and persist selection per agent. | TBD | TBD | Mohammad Shaik Fawaz | Coding | 3- Completed | 4
US-04 | T-04 | Build Agent Configuration role cards with name, role, goal, constraints, and personality. | TBD | TBD | Santanu Atta | UI | 3- Completed | 6
US-05 | T-05 | Create Negotiation State Model with scenario, round, turn, previous/current offer, status, goals, constraints, personality. | TBD | TBD | Hemalatha Bora | Backend | 2- In Progress | 8
US-06 | T-06 | Define standard Offer Structure: value/terms, agent, round, reason, timestamp. | TBD | TBD | Mohammad Shaik Fawaz | Design | 2- In Progress | 4
US-07 | T-07 | Implement rule-based Accept / Reject / Counteroffer prototype using goals and constraints. | TBD | TBD | Hemalatha Bora | Coding | 2- In Progress | 8
US-08 | T-08 | Implement concession tracking and calculate direction/size across rounds. | TBD | TBD | Santanu Atta | Santanu Atta | 2- In Progress | 5
US-09 | T-09 | Prepare Orchestrator interface for current turn, round, history, state, and next agent. | TBD | TBD | Mohammad Shaik Fawaz | Backend | 2- In Progress | 6
US-10 | T-10 | Connect scenario/agent configuration to initial negotiation state and next-turn flow. | TBD | TBD | Santanu Atta | Integration | 2- In Progress | 6
US-11 | T-11 | Update README, organize modules, and push identifiable commits to common GitHub repository. | TBD | TBD | All Interns | Documentation | 2- In Progress | 3
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
1 | Day 1 | Scenario selection, scenario data, and persona definitions completed. | Continue UI integration and validate all three scenario configurations.
1 | Day 2 | Agent Configuration UI and personality selection completed. | Connect scenario selection to agent configuration.
1 | Day 3 | Basic flow validated; negotiation state implementation started. | Finish state model and offer structure.
1 | Day 4 | Rule-based decision logic/concession tracking in progress. | Integrate orchestrator interface.
1 | Day 5 | Integration and GitHub/README work in progress. | Run end-to-end smoke test and close remaining defects.

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | 1 | TBD | TBD | Santanu Atta | Start maintaining scenario data in one shared structure. | Stop duplicating scenario definitions across UI components. | Continue using predefined scenario/persona data. | Create a single scenario configuration module.
2 | 1 | TBD | TBD | Mohammad Shaik Fawaz | Start validating personality selection against allowed options. | Stop hard-coding personality labels in multiple places. | Continue using reusable role-card components. | Centralize personality constants.
3 | 1 | TBD | TBD | Hemalatha Bora | Start documenting negotiation state transitions before coding. | Stop mixing state, offer, and decision logic in one module. | Continue writing small rule-based functions. | Separate state model, offer model, and decision engine.

## Scenario & Personas
Scenario | Agent | Role | Goal | Constraints | Personality
Vendor Pricing Negotiation | Buyer | Purchaser / Customer | Get the best possible price while meeting required quality and delivery terms. | Maximum budget; minimum quality; required delivery date. | Risk-Averse
Vendor Pricing Negotiation | Vendor | Supplier / Seller | Maximize profit while winning the deal. | Minimum acceptable price; capacity; delivery cost. | Aggressive
Job Offer Negotiation | Candidate | Job Candidate | Maximize total compensation and acceptable working conditions. | Minimum acceptable compensation; role/location requirements; joining constraints. | Collaborative
Job Offer Negotiation | Employer | Hiring Manager / Employer | Hire the right candidate within the approved compensation and policy limits. | Maximum compensation budget; role level; company policy. | Risk-Averse
Project Budget Allocation | Project Lead | Project Manager / Lead | Secure enough budget to deliver critical scope and milestones. | Total project budget; deadline; minimum resources for critical scope. | Collaborative
Project Budget Allocation | Finance Manager | Budget Owner / Finance | Control spending while funding the highest-value work. | Department/project budget cap; ROI expectations; financial policy. | Aggressive

## Workflow & Architecture
SYSTEM WORKFLOW
Scenario Selection
↓
Agent Configuration
↓
Personality Selection
↓
Negotiation State Created
↓
Orchestrator Selects Agent Turn
↓
Agent Generates Offer / Counteroffer
↓
Other Agent Evaluates
↓
Accept / Reject / Counteroffer
↓
Next Round / Negotiation Ends
↓
Outcome Report
SYSTEM ARCHITECTURE
User → Scenario Selection → Agent Configuration → Orchestrator → AI Agents → Negotiation → Outcome Report

## Negotiation Model
Field | Definition | Example
Scenario | Selected negotiation scenario. | Vendor Pricing Negotiation
Current Round | Current negotiation round number. | 2
Current Agent Turn | Agent currently expected to act. | Buyer
Previous Offer | Offer made in the immediately preceding turn. | ₹95,000
Current Offer | Latest offer under evaluation. | ₹90,000
Negotiation Status | Not Started / In Progress / Agreement / Rejected / Deadlock / Completed. | In Progress
Agent Goals | Goal(s) for each negotiating party. | Buyer: lowest acceptable price
Agent Constraints | Hard limits that must not be violated. | Buyer: maximum budget ₹100,000
Agent Personality | Aggressive / Collaborative / Risk-Averse. | Risk-Averse
Offer Structure | Offer value/terms, agent, round, reason, timestamp. | ₹90,000 ¦ Buyer ¦ R3 ¦ budget constraint ¦ timestamp
Decision | Accept / Reject / Counteroffer based on goals and constraints. | Counteroffer
Concession | Change from previous offer; direction and magnitude. | ₹95,000 → ₹90,000 = ₹5,000 concession
Orchestrator | Controls turn order, round, history, state, and next agent. | Buyer → Vendor → Buyer